## Sheet1
QuadSolver | Introduction: This project was created to write a program that solves the quadratic equation based off of user input of "a, b, c." The program was designed to model the big project that is the ultimate goal of this class, CS 4900. This story board is a template and practice so that the team can gain experience in documenting, and working together using the Extreme Programming approach to development.
CS 4900
2017-01-30
Angeloa Danducci
Jonah Groendal
Joshua Looney
Jacob Schuurmans
Story | Time(hours) | Risk(1-5) | Actual Time | % Complete
Function will receive coefficients "a,b,c" via the command prompt. | 1 | 2 |  | 100
Function will check the input, flag the user if invalid, and prompt for correct input. | 1 | 2 |  | 100
Function will calculate roots and return: (1) Two real roots, or (2) A flag saying "No Real Roots," or (3) A flag saying No Roots exist. | 1.5 | 3 |  | 100
Release 1
TOTAL | 3.5 |  | 0